Project Planning Phase
Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)
Date
15 NOV 2022
Team ID
PNT2022TMID42065
Project Name
Car Resale Value Prediction
Maximum Marks
8 Marks
Product Backlog, Sprint Schedule, and Estimation (4 Marks)
Sprint
Functional
User Story
User Story / Task
Story Points
Priority
Team
Requirement (Epic)
Number
Members
Sprint-1
Pre-process data
USN-1
Collect Dataset
1
Low
Kasilingam G
Sprint-1
USN-2
Import required libraries
1
Low
Madhan kumar R
Madhan kumar R
Sprint-1
USN-3
Read and clean data sets
2
Low
Chinnagounder
Ajaykuma
Sprint-2
Model building
USN-1
3
Medium
Split data into independent and dependent
Kasilingam G
variables
Sprint-2
USN-2
Apply using regression model
3
Medium
Venkatesan D
Sprint-3
Application building
USN-1
Build python flask application and HTML page
5
High
Madhan kumar R
Venkatesan D
Venkatesan D
 Sprint-3
USN-2
Execute and test
5
High
Chinnagounder
Ajaykumar
Kasilingam G &
Sprint-4
Training the model
USN-1
Train machine learning model
5
High
Venkatesan D
Sprint-4
USN-2
Integrate flask
5
High
Kasilingam G

---
Project Tracker, Velocity & Burndown Chart: (4 Marks)
Sprint
Duration
Sprint Start Date
Story Points
Total Story
Sprint End Date
Sprint Release Date
Completed (as on
Points
(Planned)
(Actual)
Planned End Date)
Sprint-1
20
6 Days
24 Oct 2022
29 Oct 2022
20
29 Oct 2022
Sprint-2
20
6 Days
31 Oct 2022
05 Nov 2022
20
05 Nov 2022
Sprint-3
20
6 Days
07 Nov 2022
12 Nov 2022
20
12 Nov 2022
Sprint-4
20
6 Days
14 Nov 2022
19 Nov 2022
20
19 Nov 2022
       Burndown Chart: