Project Planning Phase
Milestone and Activity List
Date
15 Nov 2022
Team ID
 PNT2022TMID42065
Project Name
 Project-Car Resale Value Prediction
Maximum Marks
2 Marks
TITLE
DESCRIPTION
DATE
Literature survey on the
21 SEPTEMBER 2022
Literature Survey &
selected project & gathering
Information Gathering
information by referring the,
technical papers, research
publications etc.
11 oct 2022
Prepare Empathy Map Canvas
Prepare Empathy Map
to capture the user Pains &
Gains, Prepare list of problem
statements
15 Oct 22
Ideation
List the by organizing the
brainstorming session and
prioritize the top 3 ideas
based on the feasibility &
importance.
Proposed Solution
Prepare the proposed solution
01 Nov 2022
document, which includes the
novelty, feasibility of idea,
business model, social impact,
scalability of solution, etc.
Prepare problem - solution fit
01 Nov 2022
Problem Solution Fit
document.
01 Nov2022
Prepare solution architecture
document.
Solution Architecture

---
Prepare the customer journey
Customer Journey
4 OCTOBER 2022
maps to understand the user
interactions & experiences
with the application (entry to
exit).
Prepare the functional
5 OCTOBER 2022
Functional Requirement
requirement document.
Prepare the
5 OCTOBER2022
Technology Architecture
technology
architecture diagram.
Draw the data flow diagrams
9 OCTOBER 2022
and submit for review.
Data Flow Diagrams
Prepare Milestone &
Prepare the milestones &
21 OCTOBER 2022
  Activity List
activity list of the project.
Develop & submit the
IN PROGRESS
Project Development -
developed code by testing it.
Delivery of Sprint-1, 2, 3 & 4